## Slide 1
BUDGETING FOR THE PROJECT
DR.LAKSHMINARAYANA SHENOY
ASSISTANT DIRECTOR
AYURVEDA RESEARCH CENTRE
MYSURU

## Slide 2
This presentation contains :
1.Preparation of budget
2.Implementation of budget
3.Monitoring of budget
4.Timeline budget
5.Risks involved in budgeting
6.Tips to Successful implementation of financial implication of the budget

## Slide 3
POINTS TO REMEMBER WHILE PREPARING BUDGET
1.Identifing the component.
2.Alot the amount to each component judiciously.
3.Alotment to the component according to rules & regulations of funding agency.
4.Spread the budget on the timeline.
5.Prepare plan for Expenditure.
6.Prepare the budget keeping in mind of inflation (6%-8%)
7.Add a component of miscellaneous, Stationary ,Institutional Expenditure to cover Unforeseen Expenditures.

## Slide 4
 | Expenditure table |  |  |  | 
SI. No | Name of component | Unit cost | No. of unit | Total | Remarks
01 | Human Resource |  |  |  | 
02 | Purchase of medicine |  |  |  | 
03 | Lab investigation |  |  |  | 
04 | Publication |  |  |  | 
05 | Stationary |  |  |  | 
06 | Contingency |  |  |  | 
07 | Miscellaneous |  |  |  | 
08 | Seminar |  |  |  | 

## Slide 5
Steps wise budget
First read the conditions of funding agency.
example:
1 RGUHS says Travel expenditure should be limited to 50000.
2.Procurement of Equipments in minor nature can be procured .
3. salary to be paid as per norms of the institutation.

## Slide 6
Timeline budget
 | 1st Year | 2nd year | Total
1.Salary for Research staff* |  |  | 
2.Working expenses** (Consumables,Contingencies,travel,etc.) |  |  | 
3.Purchase of equipment/facilities**** (Minor in nature costing not more than Rs.1.00 lakh) |  |  | 
Total |  |  | 

## Slide 7
Hands on training on budget
These are the inputs given by a funding agency to prepare a project of Ayurveda to Kalabhairaveshwara Ayurveda college, Bangalore.
2.Total budget for the project is 10 lakhs
3.30% of the budget can be used for the man power.
4.Man power is restricted to 3 persons out of which one should be Data entry operator
5.For infrastructure 20% of the budget can be used provided institution should bear 50% of the cost. 6.for lab investigation infrastructure should be given from the institution only reagents cost can be borned by the project limited to 10% of the total cost
7.Transport expenditure will be limited to 6% .
8.Institutional grand for the project will be 50% of the expenditure .
9.Total time period for the project is 05 years
Based on the above inputs prepare budget with timeline.

## Slide 8
Preparing timeline budget
List out the components first
Spread the component on timeline
If one component need more than one timeline divide the amount.
If one component needed at the end stage of the project don’t take money for the initial years.
Contengenious stationary ,miscellaneous, expenditure should be equally divided for all the years.
If one component is needed for all the three years 6%-8% of inflation can be added for subsequent years.

## Slide 9
Name of the component | 1st year | 2nd year | 3rd year | Remarks
Man power | Persons*months*Salary per month | √ | √ | 
drugs | Drugs * patients *cost per patients | √ | √ | 6-8% of the cost can be added as inflation
Publication | -- | --- | √ | At the end of the project
Transport | √ | √ | ---- | Transport is for data collection
Seminar | --- | √ | --- | Seminars amount can’t be taken at the initial stage
miscellaneous | √ | √ | √ | Divide the money equally in all quarter

## Slide 10
Points of importance
1.Collect only GST bills
2. For all expenditure Vochure is must.
3.If Vochures are not available then receipts can developed from the institutions.
4.Don’t pay cash
5.Pay by cheque or neft or DD to maintain transparency
6.Maintain a cash register.
7.Prepare a audit statement signed by a auditor.

## Slide 11
Care should be taken to maintain transparency.

## Slide 12
Take home message
1.Budget should be always in line with funding agency.
2.Timeline is must.
3.Prepare component wise budget.
4.Maintain transparency
5.Monitor progress.
Good luck

## Slide 13
Time spent here is a future investment for you
So invest Today & Harvest Tomorrow